Building a FarmBot from scratch to a functional prototype by the first week of March (approx. 7–8 weeks) is an ambitious but achievable goal if you follow a modular, concurrent development cycle.

Given your requirements, here is a realistic pipeline and procedure optimized for speed and integration.

### Phase 1: Data Strategy & Infrastructure (Weeks 1-2)

The biggest bottleneck in AI projects is the dataset. Do not wait for the bot to be built to collect data.

- Synthetic & Open Datasets: Use existing datasets like PlantVillage or CVPPP for leaf/disease classification. Use NVIDIA Isaac Sim or Unity to generate synthetic images of stems and leaf clusters to bootstrap your localization model.

- Auto-Labeling Pipeline: Use SAM (Segment Anything Model) or Grounding DINO to auto-label your custom images. You provide a prompt (e.g., "stem"), it generates masks, and you manually verify/correct them. This is 10x faster than manual labeling.

- Sensor Mocking: Write a simple Python script that mimics NPK and soil moisture data over MQTT or ROS2 topics so the UI/Logic team can work without the physical sensors.

### Phase 2: Perception Pipeline (Weeks 2-4)

Instead of separate models, use a Multi-Task Learning (MTL) architecture to save compute on the bot.

- Primary Model (The "Workhorse"): Use YOLOv11 or RT-DETR. They are state-of-the-art for real-time detection and instance segmentation.

  - Task A (Localization): Detect stem base and leaf cluster centroids.

  - Task B (Estimation): Count flowers/fruits.

- Stem Girth Logic: Use a Depth Camera (Intel RealSense or OAK-D).

  - Procedure: Segment the stem → Get the depth mask → Convert pixel width to real-world millimeters using the camera's focal length and distance-to-target.

- Yield Regression: Create a "Fusion Head." This small MLP (Multi-Layer Perceptron) takes the feature vector from the YOLO backbone + Numerical Soil Data to output a final yield estimate.

### Phase 3: Navigation & Mapping (Weeks 3-5)

RTAB-Map is robust, but the logic of "moving to each plant" needs a State Machine.

- SLAM Setup: Deploy RTAB-Map (RGB-D). It provides both a 3D point cloud and a 2D occupancy grid.

- The "Plant Node" Logic:

  - Bot explores/maps the field (Manual or Frontier Exploration).

  - The Perception model identifies a plant.

  - The coordinates are saved as a "Goal Point" in the Navigation stack (Nav2 in ROS2).

- Local Planner: Ensure you use a local planner (like TEB Local Planner) that handles uneven farm terrain and avoids "ghost obstacles" (like tall grass).

### Phase 4: Integration & Reinforcement Learning (Weeks 5-6)

Integrating RL in 8 weeks is risky. Use it for a specific, constrained task.

- The RL Component: Instead of RL for general navigation (which takes months to train), use it for Active Perception.

  - Task: If the fruit is hidden by a leaf, the RL agent controls the camera tilt/pan or the bot's micro-positioning to get a better "viewing angle" for ripeness estimation.

- Training Environment: Use Stable Baselines3 with a simplified Gymnasium environment that mimics your bot's camera movement.

### Phase 5: UI, Pruning (Bonus), & Testing (Weeks 7-8)

The UI must be the "Single Source of Truth."

- UI Stack: Use Streamlit (fastest) or Dash.

  - Integrate a live ROS2 Image stream (compressed) for the camera view.

  - Plot NPK levels on a real-time heatmap overlaid on the field map generated by RTAB-Map.

- Pruning & Ripeness (The "Stretch Goals"):

  - Ripeness: Use a simple color-space analysis (HSV) or a small ResNet classifier on the fruit crops identified in Phase 2.

  - Branch Detection: Use Skeletonization algorithms on the stem masks to find branching points.

### Critical Realistic Timeline (The "March 1st" Sprint)

| Week | Focus | Deliverable |
| --- | --- | --- |
| 1-2 | Data & Environment | Auto-labeled dataset, ROS2 Workspace setup, Simulated field. |
| 3 | Core CV Model | YOLO trained for Stem/Fruit/Leaf detection. |
| 4 | Navigation | RTAB-Map running; Bot can move from Point A to B. |
| 5 | Sensor Fusion | Girth estimation logic + Soil data integration. |
| 6 | RL & Logic | Active perception RL agent + Plant-to-plant logic. |
| 7 | UI & System Int. | Full dashboard connected to the live bot. |
| 8 | Field Testing | Bug fixes, model quantization (TensorRT) for speed. |

### Technical Tips for Success:

- Hardware Acceleration: Since you're doing Vision + SLAM + RL, you must use an NVIDIA Jetson (Orin Nano or AGX) or a laptop with a dedicated GPU. RTAB-Map and YOLO will struggle on a Raspberry Pi.

- Modular ROS2: Build every component as a separate ROS2 Node. If the RL node crashes, the Navigation and Perception nodes should still function.

- Communication: Use Micro-ROS for the soil sensors to talk directly to your main compute unit over the network.

- Depth is Key: Do not try to estimate girth or distance with a single 2D camera; the margin of error is too high for yield estimation. Use a stereo or ToF camera.

What is the specific crop you are focusing on? (The pipeline for a vineyard is very different from a cornfield, and I can refine the vision logic based on that.)

Tomato farms present a unique challenge: occlusion. Tomatoes grow in dense clusters, and vines often overlap, making "per-plant" metrics difficult.

To hit your March deadline for a Tomato FarmBot, you need to focus on Instance Segmentation rather than just Bounding Boxes. Here is your tailored pipeline for a Tomato-specific FarmBot.

### 1. The Perception Pipeline (Tomato-Specific)

In a tomato farm, stems are thin and fruit is often hidden by foliage.

- Instance Segmentation (YOLOv11-Seg): Use segmentation to separate individual tomatoes in a cluster. This is vital for yield estimation because tomatoes overlap.

  - Classes: Red_Tomato, Green_Tomato, Flower, Stem, Sucker (for pruning).

- The "Stem-Leaf Cluster" Logic:

  - Instead of looking for a plant as a whole, use a Bottom-Up approach.

  - Detect the Stem Base (where it hits the soil). This is your "Plant ID" anchor.

  - Associate all detections (fruit/leaves) within a specific radial distance of that stem anchor to that specific plant's entry in your database.

- Girth Estimation:

  - Tomatoes have hairy, non-uniform stems.

  - Procedure: Use the segmentation mask of the stem → Apply a Skeletonization algorithm (using OpenCV skimage) → Measure the width of the mask perpendicular to the skeleton at 5cm above the soil.

### 2. Yield Estimation & Soil Fusion

Tomato yield is highly predictable if you have flower counts and NPK data.

- The Yield Formula: Create a weighted regression model:

  - Yield = (Existing Fruit Count × Ripeness Weight) + (Flower Count × Pollination Probability) + (Stem Girth Coefficient).

- Soil Data Integration:

  - Tomatoes are heavy potassium (K) feeders during fruiting.

  - If your soil sensor detects low K, your UI should flag "Predicted Yield at Risk" even if the plant looks healthy now.

### 3. Navigation: The "Tomato Row" Challenge

RTAB-Map is great, but tomato greenhouses/farms are repetitive (long green rows), which can cause "Loop Closure" errors in SLAM.

- The Strategy: Use Wheel Odometry + RTAB-Map + Visual Search.

- Procedure:

  - Mapping: Drive the bot down the center of the rows. RTAB-Map creates the 3D map.

  - Waypoints: Manually or automatically tag the start and end of each row.

  - Active Alignment: As the bot moves, use the camera to "center" itself between the two rows of vines. If a leaf touches the camera, the bot should be programmed to back up and re-center.

### 4. Reinforcement Learning (RL): Active Perception

Since you want to implement RL, the most high-value use for tomatoes is "Next Best View" (NBV).

- The Problem: You can't count tomatoes hidden behind a large leaf.

- The RL Task: Train a soft actor-critic (SAC) agent to move the camera (via a small gimbal or by micro-adjustments of the bot) to maximize the "Information Gain" (i.e., finding the angle that reveals the most red pixels/fruit clusters).

- Simulation: Use Isaac Gym to simulate a tomato vine and train the agent to "peek" around leaves.

### 5. Pruning Detection (The Bonus Task)

For tomatoes, pruning usually means removing "Suckers" (the small shoots that grow in the "V" between the main stem and a branch).

- Logic:

  - Detect the Main Stem (Vertical).

  - Detect a Branch (Horizontal/Diagonal).

  - Look for a third segmentation mask in the junction. If found, label as "Sucker - Prune Required."

### 6. The UI/Dashboard (The Integration)

Your UI should be a Digital Twin of the farm.

- Map View: A 2D top-down map from RTAB-Map.

- Plant Health Cards: Clicking a point on the map pops up:

  - Ripeness Ratio: (Red vs. Green count).

  - Health Metric: Derived from Leaf Color (detecting yellowing/chlorosis).

  - Soil Status: N-P-K levels at that specific coordinate.

- Export: A "Harvest Forecast" (e.g., "Expected 50kg of tomatoes in 10 days").

### Realistic Procedure (Week-by-Week)

Weeks 1-2: Data Harvesting

- Download the "Laboro Tomato" dataset (it has high-quality instance segmentation for tomatoes).

- Supplement with your own photos of tomato stems (the most underrepresented data in open sets).

Weeks 3-4: The Perception Core

- Train YOLOv11-Seg on your classes.

- Develop the "Girth Logic" script using a Depth Camera (OAK-D is highly recommended for its built-in AI processing).

Week 5: Navigation & RTAB

- Set up RTAB-Map.

- Crucial: Use a ZED 2i or Intel RealSense D435i—the built-in IMU is necessary to keep the map stable on farm terrain.

Week 6: RL & Logic

- Implement the "Plant ID" logic (assigning data to specific locations on the map).

- Run the RL agent in simulation for camera positioning.

Week 7: UI & Stress Testing

- Build the UI with Streamlit.

- Run the bot in a real garden/farm setting. Check if "Leaf Occlusion" is breaking your count and adjust the RL agent accordingly.

### Hardware Recommendation for the AI:

- Compute: NVIDIA Jetson Orin Nano (minimum) or Orin NX.

- Camera: OAK-D Pro (The active IR helps in low light and handles dense foliage depth better than standard RGB-D).

Do you have the hardware (camera/compute) selected yet, or would you like recommendations based on your budget?

This is a 7-week sprint (concluding the first week of March). To succeed, you must work in parallel tracks: Vision, Navigation, and Integration.

Since today is January 9th, you have exactly 54 days until March 4th.

### The Master Schedule

| Week | Phase | AI & Vision Track (The "Brain") | Navigation & Robotics Track (The "Body") | Data & UI Track (The "Nerves") |
| --- | --- | --- | --- | --- |
| W1 (Jan 9) | Foundations | Download Laboro Tomato dataset. Setup YOLOv8/v11-Seg environment. | Setup ROS2 (Humble/Foxy). Calibrate Depth Camera (OAK-D/RealSense). | Setup Database (SQLite/PostgreSQL). Design UI Wireframes (Figma/Sketch). |
| W2 (Jan 16) | Core Training | Train Instance Segmentation (Fruit, Stem, Flower). Script Stem Girth logic. | Implement RTAB-Map. Perform manual mapping of a mock farm row. | Develop Micro-ROS nodes for NPK/Soil sensors. Bridge sensor data to ROS. |
| W3 (Jan 23) | Localization | Develop "Plant Anchor" logic (Linking fruit/leaves to a specific Stem ID). | Implement Nav2. Create "Waypoint Generator" to move bot between plants. | Build the UI Dashboard (Streamlit/Dash) to display live sensor feeds. |
| W4 (Jan 30) | Intelligence | Build Yield Estimation Regression (Inputs: Fruit count + Girth + NPK). | State Machine Integration: Loop (Navigate -> Stop -> Scan -> Log -> Move). | Integrate Map from RTAB-Map into the UI as a "Live Digital Twin." |
| W5 (Feb 6) | RL & Advanced | RL Implementation: Train agent for "Active Perception" (Camera tilting to see hidden fruit). | Refine "Row-Following" logic (using Vision to stay centered in tomato aisles). | Implement "Ripeness Grading" logic (HSV color analysis) and Pruning alerts. |
| W6 (Feb 13) | Integration | Quantize models (TensorRT) for Edge deployment (Jetson/Laptop). | Test "Recovery Behaviors" (What if the bot gets stuck or loses SLAM?). | Full System Sync: Ensure UI updates in real-time as the bot scans each plant. |
| W7 (Feb 20) | Field Testing | Stress test in varied lighting (Sun/Clouds). Fine-tune segmentation. | Battery/Endurance testing. Accuracy check of GPS/Map coordinates. | Final Bug Squashing. Export "Harvest Forecast" PDF/Report functionality. |
| W8 (Feb 27) | Polish | Final Demo Video recording & Documentation. | Cleanup wiring/Mechanical aesthetics. | SUBMISSION (First Week of March). |

### The Critical Path (Where projects usually fail)

#### 1. The "Plant Identity" Problem (Week 3)

- The Risk: As the bot moves, it might count the same tomato twice or assign Tomato A to Plant B.

The Fix: Use the RTAB-Map Pose. When the vision model sees a stem, record its
        (x,y,z)(x, y, z)(x,y,z)

- coordinate on the map. Any fruit detected within a 20cm radius of that coordinate is locked to that "Plant ID."

#### 2. The Reinforcement Learning (RL) Scope (Week 5)

- The Risk: Training RL for navigation takes months.

- The Fix: Limit RL to Gimbal/Camera Control only.

  - Goal: Maximize the number of segmented "Tomato" pixels in the frame.

  - Action: Tilt/Pan camera.

  - This is a small action space and can be trained in a week using a simulation or a simple "Trial and Error" script.

#### 3. Stem Girth via Depth (Week 2)

- The Fix: Don't use raw RGB. Use the Depth Map mask.

  - Get the Stem mask from YOLO.

  - Overlay this on the Depth frame.

  - Take the average depth of the stem pixels.

Use the formula:
        ActualWidth=(PixelWidth×Depth)/FocalLengthActualWidth = (PixelWidth \times Depth) / FocalLengthActualWidth=(PixelWidth×Depth)/FocalLength

  - .

#### 4. Data Fusion (Week 4)

- Your Yield Estimation model doesn't need to be a complex Deep Learning model. A Random Forest Regressor or a Gradient Boosting (XGBoost) model is perfect here.

- Inputs: [Red_Count, Green_Count, Flower_Count, Stem_Girth, Soil_N, Soil_P, Soil_K, Soil_Moisture].

- Output: Estimated_Yield_KG.

### Immediate Next Steps (Next 48 Hours)

- Hardware Check: Ensure you have a Depth Camera (OAK-D, RealSense, or Orin-compatible Stereo). You cannot do Girth estimation or RTAB-Map accurately without it.

- Dataset Acquisition: Search for the "Laboro Tomato" dataset or "OpenFruit". This will save you 2 weeks of manual labeling.

- Environment Setup: Create a Docker container or Conda environment with ROS2 Humble, Ultralytics (YOLO), and RTAB-Map.

Does this timeline align with your team's current manpower? (e.g., How many people are working on the AI vs. the Navigation?)